## Sheet2
HAWA-Tentative FAT and shipment schedule
updated date: 2017-6-7
Equipment Name | PO Status | FAT Time (Tentative) | Shipping Date (Tentative) | Arrival at Karachi Port(+40) | Arrival at Site (+20) | % complete Actual | % complete Cumulative Planned | 备注 | 预计批次
Blade 1st Batch | Issued | 2017-03-20 | 2017-05-26 | 2017-06-11 | 2017-06-26 | 54% | 49%
Tower 1st Batch | Issued | 2017-03-22 | 2017-05-09 | 2017-05-29 | 2017-06-18 | 54% | 49%
Nacelle/Hub 1st Batch | Issued | 2017-03-23 | 2017-04-11 | 2017-05-09 | 2017-05-29 | 54% | 49%
Nacelle/Hub 2nd Batch | Issued | 2017-04-11 | 2017-05-30 | 2017-07-09 | 2017-07-29 | 28% | 14% |  | 1
Nacelle/Hub 3rd Batch | Issued | 2017-04-11 | 2017-06-25 | 2017-08-04 | 2017-08-24 | 28% | 8% |  | 1
Tower 2nd Batch | Issued | 2017-04-26 | 2017-06-15 | 2017-07-25 | 2017-08-14 | 28% | 14% |  | 1
Blade 2nd Batch | Issued | 2017-04-27 | 2017-06-20 | 2017-07-30 | 2017-08-19 | 28% | 14% |  | 2
Tower 3rd Batch | Issued | 2017-06-08 | 2017-06-30 | 2017-08-09 | 2017-08-29 | 14% | 8% |  | 2
GSU, RMU | Issued | 2017-06-09 | 2017-06-25 | 2017-08-04 | 2017-08-24 | 16% | 43% |  | 2
MV. Switchgear | Issued | 2017-06-12 | 2017-06-25 | 2017-08-04 | 2017-08-24 | 16% | 24% |  | 2
Main Transformer | Issued | 2017-06-13 | 2017-06-25 | 2017-08-04 | 2017-08-24 | 16% | 27% |  | 2
Capacitor Bank | Issued | 2017-06-16 | 2017-06-25 | 2017-08-04 | 2017-08-24 | 19% | 27% | 二次及其他 | 2
Cable | NO | 2017-07-05 | 2017-07-15 | 2017-08-24 | 2017-09-13 | 10% | 26% |  | 3
Blade 3rd Batch | Issued | 2017-07-06 | 2017-07-15 | 2017-08-24 | 2017-09-13 | 14% | 8% |  | 3
Protection | Issued | 2017-07-10 | 2017-07-20 | 2017-08-29 | 2017-09-18 | 21% | 26% |  | 3
SCADA System | Issued | 2017-07-10 | 2017-07-20 | 2017-08-29 | 2017-09-18 | 21% | 26% |  | 3
132kV AIS | Issued | 2017-07-15 | 2017-07-20 | 2017-08-29 | 2017-09-18 | 16% | 24% |  | 3
DC System | Issued | / | 2017-07-20 | 2017-08-29 | 2017-09-18 | 19% | 23% |  | 3
Commutation | NO | 2017-07-30 | 2017-08-05 | 2017-09-14 | 2017-10-04 | 10% | 26% |  | 4
Metering CT/VT Protection CT/VT/CVT | Issued | 2017-08-25 | 2017-08-30 | 2017-09-29 | 2017-10-19 | 10% | 19% | 国外 | 土耳其
Surge Arrester | issued | 2017-07-01 | 2017-07-05 | 2017-08-14 | 2017-09-03 | 20% | 26% |  | 德国
CCTV | NO | / | 2017-07-30 | 2017-09-08 | 2017-09-28 | 19% | 23% |  | 5
Fire alarm System | NO | / | 2017-07-30 | 2017-09-08 | 2017-09-28 | 19% | 23% |  | 5
Anchor Cage | Issued | / | 2017-01-16 | 2017-02-26 | 2017-03-13 | 100% | 100% | 风机
Earthing Material | Issued | / | 2017-01-16 | 2017-02-26 | 2017-03-05 | 100% | 100% | 一次
Formulas:
Arrival at Site (+20) = [Arrival at Karachi Port(+40)]+15
Arrival at Karachi Port(+40) = [Shipping Date (Tentative)]+20
Note on B5: 曾珍: 船：Cerulean 15号到上海港装运
Note on B6: 曾珍: 船：RUYI 发运时间 5月9号
Note on B7: 曾珍: CHONG MING V.K1707E
Note on B8: 曾珍: 船 MV.CS FORTUNE OR SUB 5月30日发
Note on B9: 曾珍: RUYI
Note on B10: 曾珍: HANLI
Note on B11: 曾珍: YUCANG
Note on B12: 曾珍: CHONGMING
Note on B13: 曾珍: RUYI
Note on B14: 曾珍: RUYI
Note on B15: 曾珍: RUYI
Note on B16: 曾珍: RUYI
Note on D17: 曾珍: 实际日期取决于业主审批进度
Note on B18: 曾珍: CERULEAN
Note on B23: 曾珍: 业主和电网审查中
Note on B24: 曾珍: 合同已经签订，但等电网审批
Note on B25: 曾珍: from Germany
Note on B26: 曾珍: 尚未送审资料
Note on E26: 曾珍: 实际日期取决于业主审批进度
Note on B27: 曾珍: 尚未送审资料
Note on E27: 曾珍: 实际日期取决于业主审批进度

## Sheet1 (2)
Shipment and FAT schedule -HAWA Updated time：2017/5/20
SN | Description | Units | Tentative FAT Time | Venue for FAT | Remark | Batch
1 | 1st 10 units of Tower | 10 | 2017-03-22 |  | Completed
2 | 1st 10 units of WTG's nacelle | 10 | 2017-03-23 |  | Completed
3 | 1st 10 units of WTG's hub | 10 | 2017-03-23 |  | Completed
4 | 1st 10 units of WTG 's blade | 30 | 2017-03-20 |  | Completed
5 | 2nd 10 units of WTG's nacelle | 10 | 2017-04-11 |  | Completed
6 | 2nd10 units of WTG's hub | 10 | 2017-04-11 |  | Completed
7 | 2nd 10units of Tower | 10 | 2017-04-26
8 | 2nd 10units of WTG's blade | 30 | 2017-04-27
9 | 3rd 9 units of WTG's nacelle | 9 | 2017-04-11 |  | Completed
10 | 3rd 9 units of WTG's hub | 9 | 2017-04-11 |  | Completed
11 | 3rd 9 units of Tower | 9 | 2017-05-22
12 | 3rd 9 units of WTG's blade | 28 | 2017-05-27
13 | Set up Transformers | 1 lot | 2017/5/23 2017/5/24
14 | WTG Transformers | 1 lot | 2017-05-26
15 | 132kV AIS | 1 lot | 2017/5/25 2017/5/26
16 | Medium Voltage Switchgear | 1 lot | 2017-05-23
17 | Capacitor Bank | 1 lot | 2017-06-15
18 | Cable | 1 lot | 2017-06-15
19 | DC | 1 lot | /
20 | CCTV | 1 lot | /
21 | Fire alarm System | 1 lot | /
22 | Protection | 1 lot | 2017-06-22
23 | Control | 1 lot | 2017-06-23
24 | Commucation and SCADA System and Relay | 1 lot | 2017-06-24
25 | Metering HV CT/VT/CVT | 1 lot | 2017-06-25
26 | Surge Arrestor | 1 lot | 2017-06-26
27
28
Note: FAT & Shipment time is tentative and will be adjusted according to actual manufacturing progress